## Project Planner
Project Planner
| RESUME GENERATOR |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89
1 | Requirement Analysis & Planning | bar: PERIODS 1 to PERIODS 60
1.1 | Define platform objectives & scope | 1 | 1 | 1 | 1 | 100%
1.4 | Review compliance for inventory tracking | 7 | 2 | 0 | 0 | 100%
1.2 | Draft high-level feature list | 1 | 1 | 1 | 1 | 100%
1.3 | Team introduction & role assignment | 1 | 1 | 1 | 1 | 100%
1.4 | Tool setup | 1 | 1 | 1 | 1 | 100%
2 | Frontend Development | bar: PERIODS 1 to PERIODS 20
2.1 | Design resume input form | 2 | 2 | 0 | 0 | 0%
2.2 | Implement responsive UI | 4 | 2 | 0 | 0 | 0%
2.3 | Develop multiple resume templates | 6 | 1 | 0 | 0 | 0%
2.4 | Add real-time preview section | 7 | 1 | 0 | 0 | 0%
2.5 | Add export buttons in UI | 8 | 1 | 0 | 0 | 0%
3 | Backend Development | bar: PERIODS 1 to PERIODS 20
3.1 | Set up Node.js server and resume APIs | 9 | 1 | 0 | 0 | 0%
3.2 | Integrate AI API | 10 | 1 | 0 | 0 | 0%
3.3 | Build PDF/DOCX export functionality | 10 | 1 | 0 | 0 | 0%
3.4 | Setup login/auth | 11 | 1 | 0 | 0 | 0%
4 | Testing | bar: PERIODS 1 to PERIODS 20
4.1 | Manual UI and functional testing | 12 | 1 | 0 | 0 | 0%
4.2 | API and edge case testing | 13 | 1 | 0 | 0 | 0%
4.3 | Bug fixing and polish | 14 | 2 | 0 | 0 | 0%
5 | Deployment | bar: PERIODS 1 to PERIODS 20
5.1 | Build and deploy app | 16 | 2 | 0 | 0 | 0%
5.2 | Final presentation and report | 20 | 1 | 0 | 0 | 0%